## Task_Table
ID | Task Number | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | 0 | Yes | Auto Scheduled | Project Management for MS Website | 84 days? | March 4, 2025 8:00 AM | June 27, 2025 5:00 PM |  | 0 | The Project Management template plan provides a work breakdown structure that can be used to plan and schedule the effort of the Project Management activities....
1 | 1 | Yes | Auto Scheduled | Initiating | 7.5 days? | March 4, 2025 8:00 AM | March 13, 2025 12:00 PM |  | 1 | The Initiating Stage does the preliminary analysis to define the project objectives and ensures that further project work is authorized.
2 | 1.1 | Yes | Auto Scheduled | Develop Project Charter | 3.5 days? | March 4, 2025 8:00 AM | March 7, 2025 12:00 PM |  | 2 | The Project Charter is developed to formally authorize a project. The Project Charter contrains the high level definition of the project and the business justification for the project.
3 | 1.1.1 | Yes | Auto Scheduled | Identify Goals and Objectives | 1 day? | March 4, 2025 8:00 AM | March 4, 2025 5:00 PM |  | 3 | Define the primary goals and objectives for the project.
4 | 1.1.2 | Yes | Auto Scheduled | Develop Strategies and Plans | 1 day? | March 5, 2025 8:00 AM | March 5, 2025 5:00 PM | 3 | 3 | Understand the business organization and its personnel and formulate high level strategies and plans to ensure achievement of objectives.
5 | 1.1.3 | Yes | Auto Scheduled | Research Previous Experience | 1 day? | March 6, 2025 8:00 AM | March 6, 2025 5:00 PM | 4 | 3 | Research previous experience with similar projects and with similar technologies and obtain sample materials.
6 | 1.1.4 | Yes | Auto Scheduled | Develop Project Charter | 0.5 days? | March 7, 2025 8:00 AM | March 7, 2025 12:00 PM | 5 | 3 | Develop the Project Charter and present it for approval to proceed with the project.
7 | 1.2 | Yes | Auto Scheduled | Develop Preliminary Project Scope Statement | 4 days? | March 7, 2025 1:00 PM | March 13, 2025 12:00 PM | 2 | 2 | The preliminary steps necessary to develop the project's goals and objectives and secure commitment to continue the project.
8 |  | Yes | Auto Scheduled | Conduct Planning Workshop | 1 day? | March 7, 2025 1:00 PM | March 10, 2025 12:00 PM |  | 3 | Conduct an internal planning session to think through all elements of the project, identify the critical success factors, and map out the project approach.
9 |  | Yes | Auto Scheduled | Document Project Costs and Benefits | 0.5 days? | March 10, 2025 1:00 PM | March 10, 2025 5:00 PM | 8 | 3 | Perform the cost/benefit analysis for the projects. Document the cash flows, (i.e., benefits minus costs). Document the benefits and risks that cannot be assigned a cash value.
10 |  | Yes | Auto Scheduled | Develop High Level Work Breakdown Structure | 1 day? | March 11, 2025 8:00 AM | March 11, 2025 5:00 PM | 9 | 3 | Completely identify all of the work to be performed and organize the work into manageable pieces (subprojects).
11 |  | Yes | Auto Scheduled | Conduct Peer Review | 1 day? | March 12, 2025 8:00 AM | March 12, 2025 5:00 PM | 10 | 3 | Conduct a peer review session to solicit feedback on the project approach from senior delivery and management personnel from outside the project team.
12 | 1.1.1 | Yes | Auto Scheduled | Prepare Preliminary Project Scope Statement | 0.5 days? | March 13, 2025 8:00 AM | March 13, 2025 12:00 PM | 11 | 3 | Consolidate the preliminary planning material developed into the Preliminary Project Scope Statement
13 | 1.1.2 | Yes | Auto Scheduled | Planning | 27 days? | March 13, 2025 1:00 PM | April 21, 2025 12:00 PM | 1 | 1 | The Planning Stage defines the necessary steps to ensure that proper planning is done, during project start-up, before each new phase starts and as part of the change management process
14 | 1.1.3 | Yes | Auto Scheduled | Set Up Project Environment | 4 days? | March 13, 2025 1:00 PM | March 19, 2025 12:00 PM |  | 2 | Ensure that the fundamental project delivery infrastructure is in place (e.g., work space, standards and procedures, project tools).
15 | 1.1.4 | Yes | Auto Scheduled | Prepare Facilities | 1 day? | March 13, 2025 1:00 PM | March 14, 2025 12:00 PM |  | 3 | Obtain and furnish work space with the appropriate facilities.
16 | 1.2 | Yes | Auto Scheduled | Set Up Project Standards and Procedures | 1 day? | March 14, 2025 1:00 PM | March 17, 2025 12:00 PM | 15 | 3 | Define and document the specific standards and procedures to be applied on the project to ensure consistent delivery in accordance with the quality requirements.
17 |  | Yes | Auto Scheduled | Set Up Project Management Tools | 1 day? | March 17, 2025 1:00 PM | March 18, 2025 12:00 PM | 16 | 3 | Implement the project management tools to be used by the project team to manage performance.
18 | 1.1.1 | Yes | Auto Scheduled | Set Up Project Book | 1 day? | March 18, 2025 1:00 PM | March 19, 2025 12:00 PM | 17 | 3 | Collect and store the project's quality and scope control records in a standard, single location to provide familiar, rapid access to key project management information.
19 | 1.1.2 | Yes | Auto Scheduled | Define Scope | 4 days? | March 19, 2025 1:00 PM | March 25, 2025 12:00 PM | 14 | 2 | Establish the Project Scope, WBS and Deliverables necessary to ensure that the objectives defined in the Project Charter are met.
20 | 1.1.3 | Yes | Auto Scheduled | Document Scope Management Plan | 1 day? | March 19, 2025 1:00 PM | March 20, 2025 12:00 PM |  | 3 | The Scope Management Plan defines the degree of rigor to be applied to the project based on it's size, complexity, risk tolerance and organizational importance.
21 | 1.1.4 | Yes | Auto Scheduled | Specify Deliverables and Acceptance Criteria | 1 day? | March 20, 2025 1:00 PM | March 21, 2025 12:00 PM | 20 | 3 | Create a clear and unambiguous definition of each deliverable in terms of format, size and quality requirements, and specify the acceptance procedures and acceptance criteria for each deliverable.
22 | 1.2 | Yes | Auto Scheduled | Define Scope | 1 day? | March 21, 2025 1:00 PM | March 24, 2025 12:00 PM | 21 | 3 | Establish and maintain a common understanding with the customer of the scope of the project.
23 |  | Yes | Auto Scheduled | Document Assumptions | 1 day? | March 24, 2025 1:00 PM | March 25, 2025 12:00 PM | 22 | 3 | Maintain an ongoing list of the assumptions on which the estimates and schedules are based.
24 |  | Yes | Auto Scheduled | Develop Project Schedule | 5 days? | March 25, 2025 1:00 PM | April 1, 2025 12:00 PM | 19 | 2 | Identify and assign project resources, determine project activity and task dependencies, develop task estimates develop the project schedule.
25 |  | Yes | Auto Scheduled | Build Work Breakdown Structure | 1 day? | March 25, 2025 1:00 PM | March 26, 2025 12:00 PM |  | 3 | Develop the project structure in terms of detailed phases, activities, tasks, deliverables, and resources.
26 |  | Yes | Auto Scheduled | Develop Resource Plans | 1 day? | March 26, 2025 1:00 PM | March 27, 2025 12:00 PM | 25 | 3 | Identify resources (human and other) that will be required to successfully deliver the project
27 |  | Yes | Auto Scheduled | Prepare Project Estimates | 1 day? | March 27, 2025 1:00 PM | March 28, 2025 12:00 PM | 26 | 3 | Produce a detailed estimates of the costs and material resources required to deliver each component of the Work Breakdown Structure.
28 | 1.1.1 | Yes | Auto Scheduled | Define Dependencies and Develop Project Schedule | 1 day? | March 28, 2025 1:00 PM | March 31, 2025 12:00 PM | 27 | 3 | Define the milestones and phase dates for each component of the Work Breakdown Structure, and identify the dependencies between the work components (the network logic).
29 | 1.1.2 | Yes | Auto Scheduled | Document Assumptions | 1 day? | March 31, 2025 1:00 PM | April 1, 2025 12:00 PM | 28 | 3 | Maintain an ongoing list of the assumptions on which the estimates and schedules are based.
30 | 1.1.3 | Yes | Auto Scheduled | Develop Risk Plans | 3 days? | April 1, 2025 1:00 PM | April 4, 2025 12:00 PM | 24 | 2 | Identify, analyze and profile project risks,
31 | 1.1.4 | Yes | Auto Scheduled | Document Risk Management Plan | 0.5 days? | April 1, 2025 1:00 PM | April 1, 2025 5:00 PM |  | 3 | Describe the methods and procedures to be used to identify, evaluate, and eliminate or minimize project risks.
32 | 1.2 | Yes | Auto Scheduled | Identify Risks | 1 day? | April 2, 2025 8:00 AM | April 2, 2025 5:00 PM | 31 | 3 | Risk identification identifies the risks which if unmanaged could impact the project.
33 |  | Yes | Auto Scheduled | Analyze Risks | 1 day? | April 3, 2025 8:00 AM | April 3, 2025 5:00 PM | 32 | 3 | Qualitative and Quantitative Analysis of a project's risks and impacts. The result is a prioritized list of risks.
34 |  | Yes | Auto Scheduled | Document Risk Management Plans | 0.5 days? | April 4, 2025 8:00 AM | April 4, 2025 12:00 PM | 33 | 3 | Profile the potential risks to the project by producing specific plans to reduce or eliminate high risk items before they become obstacles to successful project delivery.
35 |  | Yes | Auto Scheduled | Plan for Quality | 0.5 days? | April 4, 2025 1:00 PM | April 4, 2025 5:00 PM | 30 | 2 | Prepare the way for a quality project.
36 |  | Yes | Auto Scheduled | Document Quality Management Plan | 0.5 days? | April 4, 2025 1:00 PM | April 4, 2025 5:00 PM |  | 3 | Establish the baseline against which project quality will be measured and describe the methods and procedures to be used for monitoring and verifying project quality.
37 |  | Yes | Auto Scheduled | Organize Project Resources | 2 days? | April 7, 2025 8:00 AM | April 8, 2025 5:00 PM | 35 | 2 | Identify and mobilize a productive and motivated project team.
38 |  | Yes | Auto Scheduled | Develop Organization Structure | 1 day? | April 7, 2025 8:00 AM | April 7, 2025 5:00 PM |  | 3 | Create an effective and efficient project organization structure.
39 |  | Yes | Auto Scheduled | Develop Staffing Plan | 1 day? | April 8, 2025 8:00 AM | April 8, 2025 5:00 PM | 38 | 3 | Identify the skills required for each role within the project structure, the person-day estimates and start and end dates for each role.
40 |  | Yes | Auto Scheduled | Develop Procurement Plans | 4.5 days? | April 9, 2025 8:00 AM | April 15, 2025 12:00 PM | 37 | 2 | To understand and document what needs to be purchased/contracted for the project and how the purchasing/contracting is to be done.
41 |  | Yes | Auto Scheduled | Determine Procurement Requirements | 1 day? | April 9, 2025 8:00 AM | April 9, 2025 5:00 PM |  | 3 | To understand which project components will be delivered with in-house resources and which will have to be procured from outside vendors/suppliers
42 |  | Yes | Auto Scheduled | Define Subcontractor Scope | 1 day? | April 10, 2025 8:00 AM | April 10, 2025 5:00 PM | 41 | 3 | Define the scope of work to be accomplished by each project subcontractor.
43 |  | Yes | Auto Scheduled | Identify Potential Subcontractors | 1 day? | April 11, 2025 8:00 AM | April 11, 2025 5:00 PM | 42 | 3 | To develop and qualify a shortlist of potential subcontractors for the project.
44 |  | Yes | Auto Scheduled | Identify Subcontract Type | 1 day? | April 14, 2025 8:00 AM | April 14, 2025 5:00 PM | 43 | 3 | Identify the appropriate type of contract to be used for each identified procurement requirement.
45 |  | Yes | Auto Scheduled | Document Subcontractor Management Plan | 0.5 days? | April 15, 2025 8:00 AM | April 15, 2025 12:00 PM | 44 | 3 | Describe the methods and procedures to be used in subcontracting work.
46 |  | Yes | Auto Scheduled | Develop Financial Plan | 2 days? | April 15, 2025 1:00 PM | April 17, 2025 12:00 PM | 40 | 2 | Document the expected cash flow as the basis for monitoring the monthly financial performance of the project.
47 |  | Yes | Auto Scheduled | Prepare Financial Plan | 1 day? | April 15, 2025 1:00 PM | April 16, 2025 12:00 PM |  | 3 | Translate the estimates and schedule into an expected monthly cash flow as the basis for monitoring the project's financial performance.
48 |  | Yes | Auto Scheduled | Document Assumptions | 1 day? | April 16, 2025 1:00 PM | April 17, 2025 12:00 PM | 47 | 3 | Maintain an ongoing list of the assumptions on which the estimates and schedules are based.
49 |  | Yes | Auto Scheduled | Develop Project Support Plans | 1.5 days? | April 17, 2025 1:00 PM | April 18, 2025 5:00 PM | 46 | 2 | Document the Risk, Configuration and Data Management Plans which will be used to define these aspects of the project delivery approach.
50 |  | Yes | Auto Scheduled | Document Communications Management Plan | 0.5 days? | April 17, 2025 1:00 PM | April 17, 2025 5:00 PM |  | 3 | Describe the methods and procedures to be used to identify and document the project communications requirements.
51 |  | Yes | Auto Scheduled | Document Configuration Management Plan | 0.5 days? | April 18, 2025 8:00 AM | April 18, 2025 12:00 PM | 50 | 3 | Describe the methods and procedures to be used to establish effective identification, control, accounting, and auditing of controlled items throughout the development life cycle.
52 |  | Yes | Auto Scheduled | Document Data Management Plan | 0.5 days? | April 18, 2025 1:00 PM | April 18, 2025 5:00 PM | 51 | 3 | Describe the methods and procedures to be used to implement and maintain a Data Management System for the identification, acquisition, distribution, delivery, and status reporting of data.
53 |  | Yes | Auto Scheduled | Develop Project Management Plan | 0.5 days? | April 21, 2025 8:00 AM | April 21, 2025 12:00 PM | 49 | 2 | The Project Management Plan contains the results of the Project Planning Phase and provides the definition against which the project will be delivered.
54 |  | Yes | Auto Scheduled | Document Project Management Plan | 0.5 days? | April 21, 2025 8:00 AM | April 21, 2025 12:00 PM |  | 3 | Establish the baseline for scope, budget, schedule, and quality, against which project performance is measured and all changes to the project are controlled.
55 | 3 | Yes | Auto Scheduled | Executing | 18 days? | April 21, 2025 1:00 PM | May 15, 2025 12:00 PM | 13 | 1 | Coordinating the people and other resources required to deliver the project
56 |  | Yes | Auto Scheduled | Acquire Project Team | 3 days? | April 21, 2025 1:00 PM | April 24, 2025 12:00 PM |  | 2 | Assemble, deliver team orientation and assign project responsibilities
57 |  | Yes | Auto Scheduled | Obtain Resources | 1 day? | April 21, 2025 1:00 PM | April 22, 2025 12:00 PM |  | 3 | Negotiate for resources and prepare action plans to identify any staffing deficiencies.
58 |  | Yes | Auto Scheduled | Conduct Team Orientation | 1 day? | April 22, 2025 1:00 PM | April 23, 2025 12:00 PM | 57 | 3 | Provide a formal orientation to the project and build a common understanding within the team.
59 |  | Yes | Auto Scheduled | Assign Responsibilities | 1 day? | April 23, 2025 1:00 PM | April 24, 2025 12:00 PM | 58 | 3 | Delegate responsibility for work assignments and witness commitment.
60 |  | Yes | Auto Scheduled | Direct and Manage Project Execution | 5 days? | April 24, 2025 1:00 PM | May 1, 2025 12:00 PM | 56 | 2 | Manage the data that supports the project and implement the discipline of configuration management.
61 |  | Yes | Auto Scheduled | Manage Data Items | 1 day? | April 24, 2025 1:00 PM | April 25, 2025 12:00 PM |  | 3 | Identify, control and report upon the scheduling, publishing and release of all formal data items, and the replacement of obsolete versions, in accordance with the terms of the project plan.
62 |  | Yes | Auto Scheduled | Manage Configuration Items | 1 day? | April 25, 2025 1:00 PM | April 28, 2025 12:00 PM | 61 | 3 | Identify, control, and report upon selected baseline items, such as the project description, product specifications and process specifications, which formally define the project.
63 |  | Yes | Auto Scheduled | Manage Process Data | 1 day? | April 28, 2025 1:00 PM | April 29, 2025 12:00 PM | 62 | 3 | Collect and maintain a standard set of data on the project's processes, metrics, and lessons learned.
64 |  | Yes | Auto Scheduled | Provide General Office Support | 1 day? | April 29, 2025 1:00 PM | April 30, 2025 12:00 PM | 63 | 3 | Provide general office support such as producing correspondence, document production and distribution services, and maintaining files and logs.
65 |  | Yes | Auto Scheduled | Administer Project Security Processes | 1 day? | April 30, 2025 1:00 PM | May 1, 2025 12:00 PM | 64 | 3 | Design and implement procedures to ensure adequate project security, including such things as badges, sign-in registers, electronic lock accessibility, and monitoring the security related practices in all project facilities.
66 |  | Yes | Auto Scheduled | Manage Team Performance | 2 days? | May 1, 2025 1:00 PM | May 5, 2025 12:00 PM | 60 | 2 | Optimize the performance of team members in achieving project goals.
67 |  | Yes | Auto Scheduled | Provide Team Training | 1 day? | May 1, 2025 1:00 PM | May 2, 2025 12:00 PM |  | 3 | Provide training to members of the project team (including business and subcontractor personnel) in the project-specific methodology, tools, or technology, as required.
68 |  | Yes | Auto Scheduled | Recognize Success | 1 day? | May 2, 2025 1:00 PM | May 5, 2025 12:00 PM | 67 | 3 | Develop and implement means to recognize and reward quality service, creativity, innovation, and success.
69 |  | Yes | Auto Scheduled | Assure Quality | 4 days? | May 5, 2025 1:00 PM | May 9, 2025 12:00 PM | 66 | 2 | Monitor the levels of quality being achieved.
70 |  | Yes | Auto Scheduled | Participate in Walk-throughs and Reviews | 1 day? | May 5, 2025 1:00 PM | May 6, 2025 12:00 PM |  | 3 | Participate in structured walk-throughs and reviews of project deliverables with members of the project team, to represent quality concerns.
71 |  | Yes | Auto Scheduled | Conduct Inspections and Audits | 1 day? | May 6, 2025 1:00 PM | May 7, 2025 12:00 PM | 70 | 3 | Conduct inspections and audits to determine the completeness and consistency of processes and deliverables.
72 |  | Yes | Auto Scheduled | Conduct Project Reviews | 1 day? | May 7, 2025 1:00 PM | May 8, 2025 12:00 PM | 71 | 3 | Review and appraise the project to assess and increase the probability of project success.
73 |  | Yes | Auto Scheduled | Facilitate Continuous Improvement | 1 day? | May 8, 2025 1:00 PM | May 9, 2025 12:00 PM | 72 | 3 | Investigate the causes of problems and analyze work operations to identify process improvements and reduce or eliminate failures.
74 |  | Yes | Auto Scheduled | Manage Project Communication | 1 day? | May 9, 2025 1:00 PM | May 12, 2025 12:00 PM | 69 | 2 | Develop and maintain a good working relationship with all the project stakeholders by using effective project communications.
75 |  | Yes | Auto Scheduled | Review Progress | 1 day? | May 9, 2025 1:00 PM | May 12, 2025 12:00 PM |  | 3 | Maintain frequent formal and informal contact with project stakeholders to review progress and maintain open communication.
76 |  | Yes | Auto Scheduled | Contracting with Subcontractors | 3 days? | May 12, 2025 1:00 PM | May 15, 2025 12:00 PM | 74 | 2 | Selection and management of any subcontractors required to deliver the project.
77 |  | Yes | Auto Scheduled | Issue Requisition Documents | 1 day? | May 12, 2025 1:00 PM | May 13, 2025 12:00 PM |  | 3 | Issue the formal requisition documents to prospective subcontractors.
78 |  | Yes | Auto Scheduled | Evaluate Responses | 1 day? | May 13, 2025 1:00 PM | May 14, 2025 12:00 PM | 77 | 3 | Evaluate responses to the formal requisition documents from prospective subcontractors.
79 |  | Yes | Auto Scheduled | Negotiate Subcontractor Contract | 1 day? | May 14, 2025 1:00 PM | May 15, 2025 12:00 PM | 78 | 3 | Negotiate effective contracts with subcontractors and arrange subcontract signing.
80 | 4 | Yes | Auto Scheduled | Monitoring and Controlling | 25.5 days? | May 15, 2025 1:00 PM | June 19, 2025 5:00 PM | 55 | 1 | Monitoring and measuring the project performance to ensure that the project is on target (on time, on budget meeting expectations).
81 |  | Yes | Auto Scheduled | Monitor and Control Project Work | 3 days? | May 15, 2025 1:00 PM | May 20, 2025 12:00 PM |  | 2 | Monitor and control contains the project tasks which validate the overall project direction by validating that the project work is progressing according to the plan.
82 |  | Yes | Auto Scheduled | Authorize Work | 1 day? | May 15, 2025 1:00 PM | May 16, 2025 12:00 PM |  | 3 | Delegate delivery responsibilities for a work package, establish a clear and unambiguous understanding for how the work package is to be delivered, witness commitment, and formally authorize the commencement of work.
83 |  | Yes | Auto Scheduled | Manage Action Items | 1 day? | May 16, 2025 1:00 PM | May 19, 2025 12:00 PM | 82 | 3 | Record, communicate and ensure closure on all action items including changes to the contractual baseline, requirements for information, problem reports and service requests, to facilitate effective decision-making within acceptable time frames.
84 |  | Yes | Auto Scheduled | Manage Project Records | 1 day? | May 19, 2025 1:00 PM | May 20, 2025 12:00 PM | 83 | 3 | Establish, maintain, and dispose of project records in a way that provides adequate access for team members during the project and long-term retention for use in subsequent projects.
85 |  | Yes | Auto Scheduled | Integrated Change Control | 4 days? | May 20, 2025 1:00 PM | May 26, 2025 12:00 PM | 81 | 2 | Maintain a comprehensive, clear, and measurable definition of the project scope and requirements.
86 |  | Yes | Auto Scheduled | Manage Scope | 1 day? | May 20, 2025 1:00 PM | May 21, 2025 12:00 PM |  | 3 | Establish and maintain a common understanding with the Acceptor of the scope of the project.
87 |  | Yes | Auto Scheduled | Manage Requirements | 1 day? | May 21, 2025 1:00 PM | May 22, 2025 12:00 PM | 86 | 3 | Establish and maintain a common understanding with the customer of the requirements that will be addressed by the project.
88 |  | Yes | Auto Scheduled | Control Decisions | 1 day? | May 22, 2025 1:00 PM | May 23, 2025 12:00 PM | 87 | 3 | Ensure that the project team is provided with the information and decisions necessary to keep the project on track.
89 |  | Yes | Auto Scheduled | Control Changes | 1 day? | May 23, 2025 1:00 PM | May 26, 2025 12:00 PM | 88 | 3 | Record and obtain approval for any and every change to the approved project baselines.
90 |  | Yes | Auto Scheduled | Scope Verification | 0.5 days? | May 26, 2025 1:00 PM | May 26, 2025 5:00 PM | 85 | 2 | Scope verification ensures that the project deliverables are formally accepted.
91 |  | Yes | Auto Scheduled | Manage Project Acceptance | 0.5 days? | May 26, 2025 1:00 PM | May 26, 2025 5:00 PM |  | 3 | Obtain acceptance of deliverables and final sign-off that the project has been completed.
92 |  | Yes | Auto Scheduled | Schedule Control | 3 days? | May 27, 2025 8:00 AM | May 29, 2025 5:00 PM | 90 | 2 | Maintaining the Project Schedule to ensure it remains accurate and current based on approved Change Requests and revised estimates to complete from Project Team Members.
93 |  | Yes | Auto Scheduled | Track Status | 1 day? | May 27, 2025 8:00 AM | May 27, 2025 5:00 PM |  | 3 | Track detailed progress against each activity and task, re-assess personal commitment, and re-forecast the remaining effort to completion and the expected completion date, on a regular weekly basis.
94 |  | Yes | Auto Scheduled | Maintain Project Schedule | 1 day? | May 28, 2025 8:00 AM | May 28, 2025 5:00 PM | 93 | 3 | Perform the appropriate updates to the project schedule to account for current project status, approved project changes and other project issues.
95 |  | Yes | Auto Scheduled | Maintain Work Plans | 1 day? | May 29, 2025 8:00 AM | May 29, 2025 5:00 PM | 94 | 3 | Maintain a current and reliable version of the project work plans, based on approved changes and current estimates to completion.
96 |  | Yes | Auto Scheduled | Manage Finances | 3 days? | May 30, 2025 8:00 AM | June 3, 2025 5:00 PM | 92 | 2 | Manage the monthly cash flow of the project, including the forecasted estimates to complete for the remainder of the project.
97 |  | Yes | Auto Scheduled | Monitor Cost/Schedule Variance | 1 day? | May 30, 2025 8:00 AM | May 30, 2025 5:00 PM |  | 3 | Analyze cost and schedule variances from plan and implement corrective action.
98 |  | Yes | Auto Scheduled | Control Costs | 1 day? | June 2, 2025 8:00 AM | June 2, 2025 5:00 PM | 97 | 3 | Control project costs and expenses so as deliver the project on budget.
99 |  | Yes | Auto Scheduled | Maintain Financial Plan | 1 day? | June 3, 2025 8:00 AM | June 3, 2025 5:00 PM | 98 | 3 | Reconcile the project's financial data with the corporate financial system and update the financial estimates to complete for the remainder of the project
100 |  | Yes | Auto Scheduled | Perform Quality Control | 3 days? | June 4, 2025 8:00 AM | June 6, 2025 5:00 PM | 96 | 2 | Implement and manage a program to ensure the project quality and implement continual improvement of work operations.
101 |  | Yes | Auto Scheduled | Control Quality | 1 day? | June 4, 2025 8:00 AM | June 4, 2025 5:00 PM |  | 3 | Measure and ensure that the project meets defined Quality Standards.
102 |  | Yes | Auto Scheduled | Participate in Testing | 1 day? | June 5, 2025 8:00 AM | June 5, 2025 5:00 PM | 101 | 3 | Witness testing, conduct verification testing, and conduct acceptance testing of subcontracted components.
103 |  | Yes | Auto Scheduled | Measure Quality Levels | 1 day? | June 6, 2025 8:00 AM | June 6, 2025 5:00 PM | 102 | 3 | Interpret project measurements as the basis for the continual improvement and optimization of work processes.
104 |  | Yes | Auto Scheduled | Manage Project Team | 4 days? | June 9, 2025 8:00 AM | June 12, 2025 5:00 PM | 100 | 2 | Tracking team performance, providing feedback, resolving issues and coordinating changes to the team to ensure optimal project performance.
105 |  | Yes | Auto Scheduled | Manage Communications | 1 day? | June 9, 2025 8:00 AM | June 9, 2025 5:00 PM |  | 3 | Develop and implement effective communications among all members of the project team.
106 |  | Yes | Auto Scheduled | Meet With Team | 1 day? | June 10, 2025 8:00 AM | June 10, 2025 5:00 PM | 105 | 3 | Meet regularly with team members to review status, share experiences, provide suggestions, and resolve problems and concerns.
107 |  | Yes | Auto Scheduled | Monitor Team Morale | 1 day? | June 11, 2025 8:00 AM | June 11, 2025 5:00 PM | 106 | 3 | Monitor team morale and take action to correct problem areas.
108 |  | Yes | Auto Scheduled | Conduct Team Performance Reviews | 1 day? | June 12, 2025 8:00 AM | June 12, 2025 5:00 PM | 107 | 3 | Record and communicate the accomplishments of team members, and appraise their skills, to facilitate career development.
109 |  | Yes | Auto Scheduled | Produce Performance Reports | 1 day? | June 13, 2025 8:00 AM | June 13, 2025 5:00 PM | 104 | 2 | Monitor and report on the costs, schedule, and technical performance of the project.
110 |  | Yes | Auto Scheduled | Report Weekly Status | 0.5 days? | June 13, 2025 8:00 AM | June 13, 2025 12:00 PM |  | 3 | Summarize and communicate the accomplishments for the reporting period, the objectives for the coming period, problems (if any), the status of outstanding risk items, and suggestions for dealing with issues and problems.
111 |  | Yes | Auto Scheduled | Report Monthly Status | 0.5 days? | June 13, 2025 1:00 PM | June 13, 2025 5:00 PM | 110 | 3 | Keep project status visible to Project Stakeholders by providing an appropriate summary of project status on a regular monthly basis.
112 |  | Yes | Auto Scheduled | Manage Stakeholders | 2 days? | June 16, 2025 8:00 AM | June 17, 2025 5:00 PM | 109 | 2 | All project stakeholders must be effectively communicated to to ensure a common consistent view of the project exists. It is important to ensure that the project stakeholders are satisfied with the project results.
113 |  | Yes | Auto Scheduled | Monitor Satisfaction | 1 day? | June 16, 2025 8:00 AM | June 16, 2025 5:00 PM |  | 3 | Monitor how well the stakeholder's expectations for quality service delivery are being met.
114 |  | Yes | Auto Scheduled | Resolve Issues | 1 day? | June 17, 2025 8:00 AM | June 17, 2025 5:00 PM | 113 | 3 | Identify, track and resolve issues affecting the project.
115 |  | Yes | Auto Scheduled | Risk Monitoring and Control | 1 day? | June 18, 2025 8:00 AM | June 18, 2025 5:00 PM | 112 | 2 | Managing the Risk Log and acting on Risk Management Action Plans as required to ensure the project stays on schedule.
116 |  | Yes | Auto Scheduled | Manage Risks | 1 day? | June 18, 2025 8:00 AM | June 18, 2025 5:00 PM |  | 3 | Manage the Risk Log and the Risk Action plans to ensure that risks do not impact the project.
117 |  | Yes | Auto Scheduled | Contract Administration | 1 day? | June 19, 2025 8:00 AM | June 19, 2025 5:00 PM | 115 | 2 | Ensure that all contract terms and conditions, both buyer and seller, are adhered to during the life of the contract
118 |  | Yes | Auto Scheduled | Manage Subcontractor Contract | 1 day? | June 19, 2025 8:00 AM | June 19, 2025 5:00 PM |  | 3 | Manage the relationship between the acquisition organization and the subcontracting organization.
119 |  | Yes | Auto Scheduled | Closing | 6 days? | June 20, 2025 8:00 AM | June 27, 2025 5:00 PM | 80 | 1 | Close out the project upon completion.
120 |  | Yes | Auto Scheduled | Close Project | 5 days? | June 20, 2025 8:00 AM | June 26, 2025 5:00 PM |  | 2 | Make sure that the project is properly closed down, either when project delivery is complete or when the project is terminated for whatever reason.
121 |  | Yes | Auto Scheduled | Assess Satisfaction | 1 day? | June 20, 2025 8:00 AM | June 20, 2025 5:00 PM |  | 3 | Document the overall satisfaction with the project.
122 |  | Yes | Auto Scheduled | Summarize Project Results and Lessons Learned | 1 day? | June 23, 2025 8:00 AM | June 23, 2025 5:00 PM | 121 | 3 | Work with the project team to capture relevant experience and lessons learned for the benefit of future projects.
123 |  | Yes | Auto Scheduled | Review and Recognize Team Performance | 1 day? | June 24, 2025 8:00 AM | June 24, 2025 5:00 PM | 122 | 3 | Complete performance reviews for each team member, recognize efforts and accomplishments, and celebrate success.
124 |  | Yes | Auto Scheduled | Close Out the Project Records | 1 day? | June 25, 2025 8:00 AM | June 25, 2025 5:00 PM | 123 | 3 | Update and archive project documentation and make sure that all close out conditions have been met.
125 |  | Yes | Auto Scheduled | Review and Reconcile Financial Performance | 1 day? | June 26, 2025 8:00 AM | June 26, 2025 5:00 PM | 124 | 3 | Make sure that all invoices have been delivered and all payments made.
126 |  | Yes | Auto Scheduled | Contract Closure | 1 day? | June 27, 2025 8:00 AM | June 27, 2025 5:00 PM | 120 | 2 | Blab
127 |  | Yes | Auto Scheduled | Close Contract | 1 day? | June 27, 2025 8:00 AM | June 27, 2025 5:00 PM |  | 3 | Specific actions required to ensure acceptance of deliverables, process final payments and archive and close out project contract files.

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0
1 | Project Director | P | Work |  |  |  |  | 100% | $0.00/h | 0 | Responsible for management of the project at a strategic level.
2 | Project Manager | P | Work |  |  |  |  | 100% | $0.00/h | 0 | Responsible for the delivery of a quality project on-schedule, within budget, with a satisfied Acceptor and a motivated project team.
3 | Acceptor | A | Work |  |  |  |  | 100% | $0.00/h | 0 | Key individual within the business organization who is the principal interface with the project team and who has the authority to accept all deliverables and resolve all project issues (sometimes referred to as the Project Sponsor).
4 | Application Architect | A | Work |  |  |  |  | 100% | $0.00/h | 0 | Defines the major application systems needed to support the enterprise. During systems development, the Application Architect defines the application solution.
5 | Technical Architect | T | Work |  |  |  |  | 100% | $0.00/h | 0 | Defines the technologies and standards required to support the application and information architectures. During systems development, the Technical Architect defines the technical solution.
6 | Quality Assurance Manager | Q | Work |  |  |  |  | 100% | $0.00/h | 0 | Responsible for providing confidence to management that the Quality System is being applied.
7 | Contracts Manager | C | Work |  |  |  |  | 100% | $0.00/h | 0 | Responsible for managing the contractual interfaces with the customer and with subcontractors.

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Identify Goals and Objectives | Project Director | 0 | 8h | 100%
Develop Strategies and Plans | Project Director | 0 | 8h | 100%
Research Previous Experience | Project Manager | 0 | 8h | 100%
Develop Project Charter | Project Manager | 0 | 4h | 100%
Develop Project Charter | Acceptor | 0 | 4h | 100%
Conduct Planning Workshop | Project Director | 0 | 8h | 100%
Document Project Costs and Benefits | Application Architect | 0 | 2h | 100%
Document Project Costs and Benefits | Technical Architect | 0 | 2h | 100%
Document Project Costs and Benefits | Project Manager | 0 | 4h | 100%
Develop High Level Work Breakdown Structure | Project Manager | 0 | 8h | 100%
Conduct Peer Review | Project Manager | 0 | 8h | 100%
Prepare Preliminary Project Scope Statement | Project Manager | 0 | 4h | 100%
Prepare Preliminary Project Scope Statement | Acceptor | 0 | 4h | 100%
Prepare Facilities | Project Manager | 0 | 8h | 100%
Set Up Project Standards and Procedures | Quality Assurance Manager | 0 | 8h | 100%
Set Up Project Management Tools | Project Manager | 0 | 8h | 100%
Set Up Project Book | Project Manager | 0 | 8h | 100%
Document Scope Management Plan | Project Manager | 0 | 8h | 100%
Specify Deliverables and Acceptance Criteria | Project Manager | 0 | 8h | 100%
Define Scope | Project Manager | 0 | 8h | 100%
Document Assumptions | Project Manager | 0 | 8h | 100%
Build Work Breakdown Structure | Project Manager | 0 | 8h | 100%
Develop Resource Plans | Project Manager | 0 | 8h | 100%
Prepare Project Estimates | Project Manager | 0 | 8h | 100%
Define Dependencies and Develop Project Schedule | Project Manager | 0 | 8h | 100%
Document Assumptions | Project Manager | 0 | 8h | 100%
Document Risk Management Plan | Project Manager | 0 | 4h | 100%
Document Risk Management Plan | Acceptor | 0 | 4h | 100%
Identify Risks | Project Manager | 0 | 8h | 100%
Analyze Risks | Project Manager | 0 | 8h | 100%
Document Risk Management Plans | Project Manager | 0 | 4h | 100%
Document Risk Management Plans | Acceptor | 0 | 4h | 100%
Document Quality Management Plan | Quality Assurance Manager | 0 | 4h | 100%
Document Quality Management Plan | Acceptor | 0 | 4h | 100%
Develop Organization Structure | Project Director | 0 | 8h | 100%
Develop Staffing Plan | Project Director | 0 | 8h | 100%
Determine Procurement Requirements | Contracts Manager | 0 | 8h | 100%
Define Subcontractor Scope | Contracts Manager | 0 | 8h | 100%
Identify Potential Subcontractors | Contracts Manager | 0 | 8h | 100%
Identify Subcontract Type | Contracts Manager | 0 | 8h | 100%
Document Subcontractor Management Plan | Contracts Manager | 0 | 4h | 100%
Document Subcontractor Management Plan | Acceptor | 0 | 4h | 100%
Prepare Financial Plan | Project Manager | 0 | 8h | 100%
Document Assumptions | Project Manager | 0 | 8h | 100%
Document Communications Management Plan | Project Manager | 0 | 4h | 100%
Document Communications Management Plan | Acceptor | 0 | 4h | 100%
Document Configuration Management Plan | Project Manager | 0 | 4h | 100%
Document Configuration Management Plan | Acceptor | 0 | 4h | 100%
Document Data Management Plan | Project Manager | 0 | 4h | 100%
Document Data Management Plan | Acceptor | 0 | 4h | 100%
Document Project Management Plan | Project Manager | 0 | 4h | 100%
Document Project Management Plan | Acceptor | 0 | 4h | 100%
Obtain Resources | Project Director | 0 | 8h | 100%
Conduct Team Orientation | Project Director | 0 | 8h | 100%
Assign Responsibilities | Project Manager | 0 | 8h | 100%
Manage Data Items | Project Manager | 0 | 8h | 100%
Manage Configuration Items | Project Manager | 0 | 8h | 100%
Manage Process Data | Project Manager | 0 | 8h | 100%
Provide General Office Support | Project Manager | 0 | 8h | 100%
Administer Project Security Processes | Project Manager | 0 | 8h | 100%
Provide Team Training | Project Manager | 0 | 8h | 100%
Recognize Success | Project Director | 0 | 8h | 100%
Participate in Walk-throughs and Reviews | Quality Assurance Manager | 0 | 8h | 100%
Conduct Inspections and Audits | Quality Assurance Manager | 0 | 8h | 100%
Conduct Project Reviews | Quality Assurance Manager | 0 | 8h | 100%
Facilitate Continuous Improvement | Quality Assurance Manager | 0 | 8h | 100%
Review Progress | Project Director | 0 | 8h | 100%
Issue Requisition Documents | Contracts Manager | 0 | 8h | 100%
Evaluate Responses | Contracts Manager | 0 | 8h | 100%
Negotiate Subcontractor Contract | Contracts Manager | 0 | 8h | 100%
Authorize Work | Project Manager | 0 | 8h | 100%
Manage Action Items | Project Manager | 0 | 8h | 100%
Manage Project Records | Project Manager | 0 | 8h | 100%
Manage Scope | Project Manager | 0 | 8h | 100%
Manage Requirements | Project Manager | 0 | 8h | 100%
Control Decisions | Project Manager | 0 | 8h | 100%
Control Changes | Project Manager | 0 | 8h | 100%
Manage Project Acceptance | Project Manager | 0 | 4h | 100%
Manage Project Acceptance | Acceptor | 0 | 4h | 100%
Track Status | Project Manager | 0 | 8h | 100%
Maintain Project Schedule | Project Manager | 0 | 8h | 100%
Maintain Work Plans | Project Manager | 0 | 8h | 100%
Monitor Cost/Schedule Variance | Project Manager | 0 | 8h | 100%
Control Costs | Project Director | 0 | 8h | 100%
Maintain Financial Plan | Project Director | 0 | 8h | 100%
Control Quality | Quality Assurance Manager | 0 | 8h | 100%
Participate in Testing | Quality Assurance Manager | 0 | 8h | 100%
Measure Quality Levels | Quality Assurance Manager | 0 | 8h | 100%
Manage Communications | Project Manager | 0 | 8h | 100%
Meet With Team | Project Manager | 0 | 8h | 100%
Monitor Team Morale | Project Manager | 0 | 8h | 100%
Conduct Team Performance Reviews | Project Manager | 0 | 8h | 100%
Report Weekly Status | Project Manager | 0 | 4h | 100%
Report Weekly Status | Acceptor | 0 | 4h | 100%
Report Monthly Status | Project Manager | 0 | 4h | 100%
Report Monthly Status | Acceptor | 0 | 4h | 100%
Monitor Satisfaction | Project Director | 0 | 8h | 100%
Resolve Issues | Project Director | 0 | 8h | 100%
Manage Risks | Project Manager | 0 | 8h | 100%
Manage Subcontractor Contract | Contracts Manager | 0 | 8h | 100%
Assess Satisfaction | Project Manager | 0 | 8h | 100%
Summarize Project Results and Lessons Learned | Project Manager | 0 | 8h | 100%
Review and Recognize Team Performance | Project Manager | 0 | 8h | 100%
Close Out the Project Records | Project Manager | 0 | 8h | 100%
Review and Reconcile Financial Performance | Project Manager | 0 | 8h | 100%
Close Contract | Contracts Manager | 0 | 8h | 100%